Name : Ansari M.Saeem M.Saleem
Uid : 2019430001
Subject : PM - ISE
Aim : Case Study on failure of Project Stretch

About Project Stretch :
This was developed by the International Business Machines (IBM) Corporation at Poughkeepsie, N.Y. started toward the end of 1954.the project was directed more specifically toward achieving, on very large mathematical computing problems, the highest performance possible within certain limits of time and resources. If mostly on-the-shelf components were used, a factor-of-l0 improvement over the IBM 704, the fastest computer then in production, appeared feasible. Although this leve1 of improvement would have been a respectable achievement, it was rejected as not being a large enough step. Instead, an over-al1 performance of 100 times that of the 704 was set as the target.
The purpose of setting so ambitious a, goal was to stimulate innovation in al1 aspects of computer design. The technology available in 1955 was clearly not adequate for the task. New transistors, new cores, new logical features, and new manufacturing techniques were needed, which, although they did not yet exist, were known to least physically possible. Even though the goal might not be reached in all respects, the resultant machine would set a new standard of performance and make available t'he best technology that could be achieved by straining the technical resources of the laboratory. Hence the name Project Stretch.
Objectives of Project Stretch :
The early design objectives were described in 1956' in terms of certain technological and organizational goals:
1. Performance : An over-al1 performance leve1 of 100 times that of the fastest machines then in existence was the genera1 objective. (It has since become evident that speed comparisons of widely different machines are very difficult to make, so that it is hard to ascertain how well this target has been achieved. Lsing the IBM 704 as the reference point, and assuming problems that can easily be fitted to the shorter word size, the smaller memory, and the more limited repertoire of the 704, the speed ratio for the computer actually built falls below the target of 100. On the other hand, for large problems which strain the facilities of the 704 in one or more ways, the ratio may exceed 100.)
2. Reliability : Solid-state components promised t'he much higher reliability needed for satisfactory operation of a necessarily complex machine.
3. Checking Errors: Extensive automatic checking facilities were intended to detect any errors that occurred and to locate faults within narrow limits. Storage devices were also to be equipped with error-correction facilities to ensure that data could be recovered in spite of an occasiona1 error.
4. High-speed Arithmetic : A high-speed parallel arithmetic unit was to execute floating-point additions in 0.8 microsecond and multiplications in 1.4 microseconds. (The actual speeds are not as high, see Chap. 14.) This unit would not be responsible for instruction preparation, indexing, and operand fetching, which were to be carried out by other sections of the system whose operation would overlap the arithmetic.
5. Editing : A separate seria1 computer unit with independent instruction sequencing was visualized to edit input and output data of variable length in a highly flexible manner. (It was later found desirable to combine the seria1 and parallel units to a greater degree, so that they are no longer independent, but the functional capability of both units was retained.)
6. Memory : The main memory was to have a cycle time of only 2 microseconds. (Al1 but the early product'ion memories will indeed be capable of working a t 2.0 psec, but computer timing dictates a slightly longer cycle of 2.1 psec.) The capacity was to be 8,192 (later raised to 16,384) words per unit.
7. Input-Output Exchange : A unit resembling somewhat a telephone exchange was to provide simu1taneous operation of all kinds of input-output, storage, and data transmission devices.

Reason for failure :
Following are the issues that cause failure to project Stretch:
- Goal was not realistic, because at that time technology was not as advance as its should to make a supercomputer.
- The team lacks the Subject Matter Expertise needed to complete the project successfully because at that time filed was totally new.
- Project goal was to achieve a supercomputer that would be 100 time faster than the existing one but it failed to achieve its primary goals.
- There were not enough resources to fulfill the requirement.
- The fundamental transistor circuit and memory registers are slower.

Actions to mitigate the failure:

Technical feasibility:

Conclusion:
As software has become integral part of every product and process so there is a need to make a full proof system so that the software failures could be avoided. There is further requirement of root cause analysis of these software failures to understand the problematic area and suggest the areas of improvement in the current process as several corrective & preventive actions needs to be taken while developing products and software systems.